| January – February 2018 |  | March – April 2018 | May – July 2018 | August – December 2018 | January – September 2019 |
| --- | --- | --- | --- | --- | --- |
| Regional | CH(N)A Deliverables: - 2018 WNC Healthy Impact Celebration and Kickoff regional event for all hospitals and public health agencies (Jan 26th at UNC Asheville) - SOTCH scorecard support available, including SOTCH Study Hall / work session (Feb 2nd at WNC Health Network) - Finalize region-wide CH(N)A data collection scope, content, and timeline - Finalize Regional Community Phone survey (Jan 31st) - Begin Regional Community Phone survey data collection mid-February - Request 211 Health Resource Inventory info - Update WNC Healthy Impact materials and website to reflect new cycle RBA and Implementation Support: - Getting to Results: Quarterly Performance Measure Workshops (rescheduled due to weather – Feb 22nd) - Monthly Study Halls (Jan 16th and Feb 2nd at WNC Health Network) | CH(N)A Deliverables: - Begin updating 2018 secondary data set. - Finalize secondary dataset/ list of measures - Create CHA and CHNA base templates - Distribute guidance on local secondary data sources; at-risk/vulnerable populations; local primary data collection (e.g. listening sessions); health resource inventory & 211 datasets RBA and Implementation Support: - Local Data Collection Training (March 2nd) - Getting to Results: Performance Measure Workshops (April 19th, Haywood County HHS) - Social Determinants of Health Convening (April 13th, Western Carolina University at Biltmore Park in Asheville) (3rd in series of TA Package and Tools Convenings for regional priorities) - Monthly Study Halls (March 28th, April 25th “Measuring Collaborative Meeting Effectiveness”) | CH(N)A Deliverables: - Begin collecting online key informant surveys - Complete collection of 2018 Regional Community Health Survey and online key informant surveys (to be released 8/18) - Complete update of 2018 secondary data set (to be released 8/18) - Prepare county-specific data reports/CH(N)A templates - Prepare county-specific data PPT slides - Compile set of census level data/maps for county distribution RBA and Implementation Support: - Results for Health Conference, co-hosted by WNCHN and Clear Impact (May 16-18 in Asheville) - Listening to Community Training (June 8th at Habitat Conference Room, Asheville, NC) - Monthly Study Halls (July, TBD) | CH(N)A Deliverables: - WNC Healthy Impact data (Regional Community Phone Survey results, key informant interview summaries, and secondary data set), reports, and templates shared locally Aug. 17th, 2018. - Regional data orientation event to support local use of data provided (August 17th, 2018) - PowerPoint Slide template provided on CH(N)A process & Healthy Impact for use locally RBA and Implementation Support: - Support for prioritization and action planning (TBD) | CH(N)A Deliverables: - Regional data presentation and report distribution - Collect local priorities from communities; analyze to inform regional priority health issues - Support available for CHA and CHNA final reporting - Community Health Improvement Plan (CHIP) template and support provided (date TBD) RBA and Implementation Support: - Support for action planning and CHIP (TBD) |
| See next page for ONGOING local and regional opportunities and expectations Local – Public Health and Hospital | Public Health - Reach out to hospital partners (staff and leadership) and lead partner conversations as needed - Establish and convene local CH(N)A team, including hospital partners - Lead local process for selecting additional questions for Regional Community Health Survey (due January 30th) Hospitals - Participate in partner conversations with public health - Participate in external (community-wide) hospital/health department/key partner CH(N)A team and shared process - Engage with public health partners on local process for selecting additional questions for Regional Community Phone Survey (due Jan 30th) - Engage with public health on participants for key informant survey - Clarify and engage internal hospital CHNA team (finance, compliance, community benefit, population/ community health) to help guide CHNA and internal deadlines & process | Public Health - Submit 2017 State of the County’s Health report (SOTCH) to NC DPH by March 5th and post online - Plan and implement additional local data collection as preferred/needed – local secondary data, listening sessions, additional key informant interviews, etc. - Partner to review health facilities, resources, and gaps; discuss with CH(N)A team - Lead local process for participant list for key informant online survey Hospitals - Review 2017 State of the County’s Health report (SOTCH) as provided by public health partners - Support planning and implementation of additional local data collection as needed/preferred, including internal/hospital data for CH(N)A - Partner to review health facilities, resources, and gaps; discuss with CH(N)A team | Public Health - Review and update 2-1-1 County Resource List - Compile, analyze, and interpret additional local data if collected - Begin to design plan for (internal & external) review of data and establishing priorities with hospital(s) and other key partners/ community stakeholders Hospitals - Help review and update 2-1-1 County Resource List - Help compile, analyze, and interpret additional local data as preferred/needed - Discuss plans/ideas (internal & external) for review of data and establishing priorities with health department(s) and other key partners/ stakeholders | Public Health - Review county-level data reports internally and with key partners - Data interpretation - Lead local community priority setting process Hospitals - Review county-level data reports internally and with key partners - Data interpretation - Collaborate on local community priority setting process | Public Health - Complete local CHA template - Submit completed CHA to the NC Division of Public Health (due March 2019) Hospitals - Support completion as needed/ review county-specific CHA - Complete hospital facility-specific CHNA executive summary based on one or more county-specific CHAs - Get approval by authorized body of the hospital facility and post CHNA on website (Timing varies by facility – suggest early 2019) |
| Ongoing Regional & Local | Regional Ongoing: - Convene regional workgroups and partners (Data, Communications, RBA and temporary ad-hoc workgroups as needed) - Continued support for Scorecard and Performance Measures, including Monthly “Performance Measure Workshops & Study Halls” - Hospital/Public Health support/training provided as requested on RBA basics & specific use of RBA and scorecard within the community health improvement cycle (CHA/CHIP) Hospitals and Public Health Agencies Ongoing: Focus on performance measures, improvement and alignment: - Attend performance measure study halls, Getting to Results Training, request technical assistance and/or tailored training for your agency. - Continue development/implementation of e-CHIP (public health) and hospital implementation strategy (hospital) with performance measures and partnership/alignment within community-wide CHIP process. Request WNCHN support as needed. - Use performance measure data to identify improvement needs to continue working towards anticipated program results. Reach out: - Meet/communicate (internally and with partners) to review plan progress/performance of specific programs & strategies. - Request agency-tailored or community-wide RBA training from WNC Health Network as needed. - Establish and/or continue regular meetings w/ public health & hospital (leadership & staff), assuring alignment/integration of hospital strategies in e-CHIP. - Establish and/or continue internal conversations among staff within your agency that help lead/implement this work locally. - Continue identifying opportunities for meaningful community engagement in the health improvement process. - Share any updates to local stories page: www.WNCHealthyImpact.com - Participate in regional workgroups (Data, Communications, RBA and temporary ad-hoc workgroups as needed) |  |  |  |  |

Contact Marian.Arledge@WNCHN.org with questions or comments. Please visit WNCHN.org and WNCHealthyImpact.com to learn more